## Week 1
Tasks | Location | Monday |  |  | Tuesday |  |  | Wednesday |  |  | Thursday
|  | Morning | Afternoon | Evening | Morning | Afternoon | Evening | Morning | Afternoon | Evening | Morning | Afternoon | Evening
DW labelling | Field | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1/2 | Team 1/2 | Team 1/2
DW meaures | Field | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1/2 | Team 1/2 | Team 1/2
Cutting discs | Field | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1/2 | Team 1/2 | Team 1/2
Put mesh under DW | Field | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1/2 | Team 1/2 | Team 1/2
Measure fresh weight Disc | Hostel | Team 1/2 | Team 1/2 | Team 1/2 | Team 1/2 | Team 1/2 | Team 1/2 | Team 1/2 | Team 1/2 | Team 1/2 | Team 1/2 | Team 1/2 | Team 1/2
Sensors calibration | Hostel | Team 2 | Team 2 | Team 2 | Team 2
Chambers implementation | Hostel | Team 2 | Team 2 | Team 2 | Team 2
Tests silicone collars | Hostel | Team 2 | Team 2 | Team 2 | Team 2
Buy silicone and other things | Brasov |  |  | Team 2 | Team 2
Sensors Instalation | Field |  |  |  | Team 2 | Team 2 | Team 2 | Team 2 | Team 2 | Team 2 | Team 2 | Team 2 | Team 2
Collars installation | Field |  |  |  | Team 2 | Team 2 | Team 2 | Team 2 | Team 2 | Team 2 | Team 2 | Team 2 | Team 2
Team 1 | Ana P, Ana H, Student 1, Student 2/Catalin
Team 2 | Javi, Nagore, Jorge, Student 2/Catalin
Brief explanation
DW labelling | Staple the tag to the DW piece
DW meaures | Dimanesions of the DW piece
Cutting discs | Chainsaw cutting
Put mesh under DW | Cut pieces with scissors and put them under DW
Measure fresh weight Disc | IN the hostel, weight the discs
Sensors calibration | Calibrate different sensors
Chambers implementation | Finish the buiding of Nagore´s chambers
Tests silicone collars | Tests for the best way to install collars over the 25d DW
Buy silicone and other things | We need to buy more silicone, probably
Sensors Instalation | We need to have the drilling machine to do it?
Collars installation | Install collars in 25d DW

## Week 2
Tasks | Location | Monday |  |  | Tuesday |  |  | Wednesday |  |  | Thursday
|  | Morning | Afternoon | Evening | Morning | Afternoon | Evening | Morning | Afternoon | Evening | Morning | Afternoon | Evening
Measure DW respiration | Field | Team 2 | Team 2 | Team 2 | Team 2 | Team 2 | Team 2 | Team 2 | Team 2 | Team 2 | Team 2 | Team 2 | Team 2
Dry samples in Lab | Lab | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1
Prepare samples for analytical services | Lab | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1 | Team 1
Measure DW respiration | Do the different diel curves of CO2 fluxes from DW
Dry samples in Lab | Put samples in oven abd weight them dry
Prepare samples for analytical services | Cut subsamples from discs to send to Spain