Field protocol DEEWOOD:

Task 0. Prepare material to bring to the field.

Collect material for field campaigns. E.g. instrumentation, notebooks, markers, pens, sensors and chambers, chainsaw, zipbags,

Task1. Cut sub-samples of wood from samples that will be left in Sinca (1 day)

Cut discs of 10 cm (h) of all deadwood (DW) samples before installation in forest.

Material needed:

Chainsaw

Zipbags

Marker

Task2. Weight samples and put samples in place (1 day)

Weight samples before install them in forest

Material needed:

Scale

Task 3. Install sensors (3 days)

Sensors should be installed in soil (TMS4) and DW material. These sensors will register air and wood climatic conditions in real time (continuously)

Material needed:

Sensors

Cable

Dataloggers

Batteries

Task 4. Measure CO2 (2 days)

Measure CO2 fluxes from DW material. We will perform campaigns of CO2 production at different times during the day to obtain diel cycles of CO2

Material needed:

EGM-4

Collars

Expansive foam to install collars

Chambers

Task 5. Post- field campaign sampling processing: prepare samples to be sent to Spain (Raquel) and other external analyses (4 days?)

Back to Brasov. We will need to pre-process the DW samples for their shipment to the different analytic services.

Material needed:

Digital scales

Ball mill

Zipbags

…..

Task 6. Ship samples (3 days)